## 1. Product Overview
Item | Description
Product Name | Virtual Shirt Try-On System
Product Vision / Purpose | To help online shoppers visualize how shirts will look and fit on them in real-time using AI and AR, increasing purchase confidence and reducing product returns.
Business Goals / Key Success Factors | • Improve online conversion rates for apparel retailers • Reduce size-related returns and customer dissatisfaction • Provide a seamless and interactive virtual try-on experience • Enable small boutiques to adopt affordable AR technology
Primary Stakeholders | • Online Shoppers (18–35 years) • Small and mid-sized apparel retailers • Fashion brands using Instagram Shops/Shopify • Product Development Team • Retail Store Owners like The Urban Streetwear

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | User Authentication | US1 | As a user, I want to sign up using email/OTP so that I can access the virtual try-on features securely. | Registration screen design | Must Have | 8 | To Do | Backend Dev | Verify OTP flow | completed
|  |  |  | Email/OTP validation |  |  |  |  | Validate login input
Login screen
OTP generation & verification
Forgot password
|  | US2 | As a returning user, I want to log in quickly so I can resume my try-on sessions. | Login API | Should Have | 5 | To Do | Backend Dev | Login success test | completed
|  |  |  | Session management |  |  |  |  | Session timeout test
Error handling
|  | US7 | As a shop owner, I want secure access to the admin panel so I can upload shirt models. | Admin login module | Must Have | 8 | To Do | Backend Dev | Admin access test | completed
Access control
Token validation
Epic ID | Epic Title | User Story ID | User Story / Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
E2 | Dashboard & AR Try-On | US5 | As a user, I want to view my live webcam feed on the dashboard so I can see the try-on preview. | Webcam access API Camera permission handling Live video rendering | Must Have | 13 | In Progress | Frontend Dev | Webcam test Permission check | completed
|  | US6 | As a user, I want to select a shirt and see it overlaid on my body in real-time. | Pose detection model Shirt overlay logic Canvas rendering Scaling & rotation algorithm | Must Have | 21 | To Do | AI/AR Dev | Shirt alignment test FPS performance tests | completed
|  | US3 | As a user, I want to switch between different shirt designs easily. | Shirt selector UI Image preloading Asset manager | Should Have | 8 | To Do | Frontend Dev | UI switch test Asset load speed test | completed
|  | US4 | As a shop owner, I want to upload my own shirt images to the catalog. | Image upload API File validation Storage handling | Could Have | 5 | To Do | Backend Dev | Upload test Format validation test | completed
Epic ID | Epic Title | User Story ID | User Story / Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
E3 | Product Catalog & Categories | US8 | As a user, I want to view shirts categorized by type so I can find products easily. | Category table Category filter UI API to fetch categories | Must Have | 8 | To Do | Backend Dev | Verify category filtering | completed
|  | US9 | As a user, I want to filter shirts by size so I can select the right fit. | Size metadata (S, M, L, XL) Filter logic | Must Have | 8 | To Do | Backend Dev | Validate size filter | completed
|  | US10 | As a shop owner, I want to add product categories like Casual, Formal, Party Wear. | Category CRUD APIs Admin UI | Should Have | 5 | To Do | Backend Dev | Category add/edit test | completed
Epic ID | Epic Title | User Story ID | User Story / Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
E4 | Product Management | US11 | As a user, I want to view detailed product information before trying it on. | Product detail page Shirt description Price display | Must Have | 8 | To Do | Frontend Dev | Product details render test | completed
|  | US12 | As a shop owner, I want to add new shirt products with size and category details. | Product add form Image + metadata storage | Must Have | 13 | To Do | Backend Dev | Product creation test | completed
|  | US13 | As a user, I want to see multiple color options for a shirt. | Color variants mapping UI selector | Should Have | 5 | To Do | Frontend Dev | Color switch test | completed
Epic ID | Epic Title | User Story ID | User Story / Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
E5 | Orders & Payments | US14 | As a user, I want to add shirts to cart so I can place an order. | Cart service Session storage | Must Have | 8 | To Do | Backend Dev | Add-to-cart test | completed
|  | US15 | As a user, I want to make secure payments for my order. | Payment gateway integration (Razorpay/Stripe) | Must Have | 13 | To Do | Backend Dev | Payment success/failure test | completed
|  | US16 | As a user, I want to view my order history. | Orders table Order status API | Should Have | 5 | To Do | Backend Dev | Order history test | completed
|  | US17 | As a shop owner, I want to manage orders and update delivery status. | Admin order dashboard Status update API | Could Have | 5 | To Do | Backend Dev | Order status update test | full not updated
Epic ID | Epic Title | User Story ID | User Story / Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
E6 | Inventory Management | US18 | As a shop owner, I want to manage stock quantity for each size. | Inventory table Stock update API | Should Have | 8 | To Do | Backend Dev | Stock update test | not updated
|  | US19 | As a user, I want to see if a size is out of stock before ordering. | Stock availability check | Should Have | 5 | To Do | Frontend Dev | Out-of-stock UI test | not updated

## 3. Roadmap
Release | Target Date | Key Features (List Epic Names) | Dependencies | Demo Status
v0.1 | 2025-11-15 | Authentication, Basic AR Try-On (Shoulder Tracking), Dashboard MVP | Ai models | Completed
v0.2 | 2025-11-22 | Enhanced Shirt Overlay, Shirt Selection UI, Asset Loader | Shirt assets | Completed
v0.3 | 2025-11-29 | Pose Detection Upgrade (MoveNet), Scaling & Rotation Fix | Model optimization | Completed
v0.4 | 2025-12-02 | Shirt Upload (Admin Module), Product Catalog, Categories & Sizes | Backend storage | Completed
v0.5 | 2025-12-05 | Try-On Analytics (Usage Count, Engagement Metrics) | Dashboard API | Completed
v1.0 | 2025-12-10 | Product Listing, Cart, Secure Payment Integration, UI Polish | Payment gateway | Completed
v1.1 | 2025-12-27 | Order Tracking, Order Status Updates, Performance Optimization | Order service API | In Progress

## 4. Retrospective
What Went Well | What Didn’t Go Well | Improvements / Action Items (Next time what will you do differently) | Owner
Strong team collaboration enabled timely completion of MVP features | Initial instability in pose detection accuracy | Fine-tune pose detection thresholds and validate with more real-world test cases | AI/AR Developer
Smooth integration of authentication, product catalog, and AR try-on | Delay in receiving some product assets | Define stricter asset submission timelines and validation checklist | Design Lead
Stable webcam integration and improved overlay performance | Mobile browser testing started late | Include mobile-first testing from the first sprint | Frontend Developer
Successful integration of cart and payment gateway | Order tracking implementation took longer than expected | Break order-tracking into smaller tasks and start earlier | Backend Developer
Clear communication with stakeholders and mentor feedback | Limited analytics data during early sprints | Integrate analytics tracking from the initial development phase | Product Manager